## Project 2 Gantt Chart
Project 3: Visualize (FHWA)
Task | Assigned To | Start Date | End Date | Duration (Days) | 02-26 | 02-27 | 02-28 | 03-01 | 03-02 | 03-03 | 03-04 | 03-05 | 03-06 | 03-07 | 03-08 | 03-09 | 03-10 | 03-11 | 03-12 | 03-13 | 03-14 | 03-15 | 03-16 | 03-17 | 03-18 | 03-19 | 03-20 | 03-21 | 03-22 | 03-23 | 03-24 | 03-25 | 03-26 | 03-27 | 03-28 | 03-29 | 03-30 | 03-31
Review NHTS metadata & codebook | Marissa Faue | 2026-02-26 | 2026-02-28 | 3 | bar: 02-26 to 02-28
Review NGSIM metadata & codebook | Daniel Kugler | 2026-02-26 | 2026-02-28 | 3 | bar: 02-26 to 02-28
Select variables for all plots (NHTS + NGSIM) (Depends: Metadata review) | All | 2026-03-01 | 2026-03-02 | 2 | bar: 03-01 to 03-02
Set up repo + folder structure + imports (Depends: Variable selection) | Kaleb Mangers | 2026-03-01 | 2026-03-03 | 3 | bar: 03-01 to 03-03
Import CSV files into Python (Depends: Repo setup) | Kaleb Mangers | 2026-03-03 | 2026-03-04 | 2 | bar: 03-03 to 03-04
Clean NHTS dataset (missing values, datatypes) (Depends: Import complete) | Marissa Faue | 2026-03-04 | 2026-03-08 | 5 | bar: 03-04 to 03-08
Clean NGSIM dataset (filtering, formatting, time fields) (Depends: Import complete) | Remy Balderas Izaguirre | 2026-03-04 | 2026-03-08 | 5 | bar: 03-04 to 03-08
Verify cleaned datasets + save final versions (Depends: Cleaning complete) | All | 2026-03-09 | 2026-03-10 | 2 | bar: 03-09 to 03-10
Bar chart (categories within a variable) (Depends: Clean data) | Daniel Kugler | 2026-03-11 | 2026-03-13 | 3 | bar: 03-11 to 03-13
Histogram (distribution of a variable) (Depends: Clean data) | Marissa Faue | 2026-03-11 | 2026-03-14 | 4 | bar: 03-11 to 03-14
Boxplot (distribution by category) (Depends: Clean data) | Kaleb Mangers | 2026-03-12 | 2026-03-15 | 4 | bar: 03-12 to 03-15
Time-series plot #1 (driving behavior) (Depends: Clean data) | Remy Balderas Izaguirre | 2026-03-13 | 2026-03-17 | 5 | bar: 03-13 to 03-17
Time-series plot #2 (driving behavior) (Depends: Clean data) | Marissa Faue | 2026-03-15 | 2026-03-18 | 4 | bar: 03-15 to 03-18
Customize at least one plot (matplotlib/seaborn styling) (Depends: Plot created) | Marissa Faue | 2026-03-16 | 2026-03-18 | 3 | bar: 03-16 to 03-18
Research Intelligent Driver Model (IDM) requirements (Depends: Clean NGSIM) | Kaleb Mangers | 2026-03-18 | 2026-03-20 | 3 | bar: 03-18 to 03-20
Code IDM simulation + baseline parameters (Depends: IDM research) | Daniel Kugler | 2026-03-20 | 2026-03-24 | 5 | bar: 03-20 to 03-24
Test simulation runs + debug (Depends: Simulation code) | Remy Balderas Izaguirre | 2026-03-24 | 2026-03-26 | 3 | bar: 03-24 to 03-26
Visualize trajectories / behavior outputs (Depends: Simulation complete) | Marissa Faue | 2026-03-25 | 2026-03-27 | 3 | bar: 03-25 to 03-27
Annotated code document (line-by-line explanation) (Depends: Code finalized) | Marissa Faue | 2026-03-24 | 2026-03-29 | 6 | bar: 03-24 to 03-29
Scope of Work (variables + plan + explanation) (Depends: Variables finalized) | Daniel Kugler | 2026-03-25 | 2026-03-29 | 5 | bar: 03-25 to 03-29
Technical report draft (Intro/Methods/Results) (Depends: Plots complete) | All | 2026-03-26 | 2026-03-30 | 5 | bar: 03-26 to 03-30
GitHub repo finalization + upload data/code (Depends: Code finalized) | Remy Balderas Izaguirre | 2026-03-27 | 2026-03-30 | 4 | bar: 03-27 to 03-30
README (summary + user guide for prompts) (Depends: GitHub setup) | Kaleb Mangers | 2026-03-28 | 2026-03-30 | 3 | bar: 03-28 to 03-30
Timesheet completion (hours by task & person) (Depends: Task completion) | All | 2026-03-30 | 2026-03-31 | 2 | bar: 03-30 to 03-31
Final review + submit to Canvas (Depends: All deliverables complete) | All | 2026-03-31 | 2026-03-31 | 1 | bar: 03-31